## Sheet1
Development Log
Column1 | Column2 | Column3
DOMAIN NAME: | Machine Learning
INTERN NAME: | Faraj Momin
DOCUMENT NAME: | Development Log
Intern ID | IP - 4039
SL. No | Feature Name | Version 1 Creation Date | Version 1 Link | Version 2 link | Version 2 Creation Date | Version Change Description | Development Status | Review Status | Comments
Task1: Placement Status Prediction
1 | Data Loading | 2024-07-28 | https://colab.research.google.com/drive/1j2OLXF8QNEvRq_0Nb0xtKzC_0NCx4QkU?usp=sharing | N/A | N/A | None | Completed | Reviewd | None
2 | Data Cleaning | 2024-07-28 | https://colab.research.google.com/drive/1j2OLXF8QNEvRq_0Nb0xtKzC_0NCx4QkU?usp=sharing | N/A | N/A | None | Completed | Reviewd | None
3 | Data Modeling | 2024-07-28 | https://colab.research.google.com/drive/1j2OLXF8QNEvRq_0Nb0xtKzC_0NCx4QkU?usp=sharing | N/A | N/A | None | Completed | Reviewd | None
4 | Splitting | 2024-07-28 | https://colab.research.google.com/drive/1j2OLXF8QNEvRq_0Nb0xtKzC_0NCx4QkU?usp=sharing | N/A | N/A | None | Completed | Reviewd | None
5 | Data Visualization | 2024-07-28 | https://colab.research.google.com/drive/1j2OLXF8QNEvRq_0Nb0xtKzC_0NCx4QkU?usp=sharing | N/A | N/A | None | Completed | Reviewd | None
6 | Prediction | 2024-07-28 | https://colab.research.google.com/drive/1j2OLXF8QNEvRq_0Nb0xtKzC_0NCx4QkU?usp=sharing | N/A | N/A | None | Completed | Reviewd | None
Task 2 :Year Of Graduation Prediction
1 | Data Loading | 2024-07-28 | https://colab.research.google.com/drive/18Lo3BwAuiaqpXztKGXxk5LHCURsm-_8K?usp=sharing | N/A | N/A | None | Completed | Reviewd | None
2 | Data Cleaning | 2024-07-28 | https://colab.research.google.com/drive/18Lo3BwAuiaqpXztKGXxk5LHCURsm-_8K?usp=sharing | N/A | N/A | None | Completed | Reviewd | None
3 | Data Modeling | 2024-07-28 | https://colab.research.google.com/drive/18Lo3BwAuiaqpXztKGXxk5LHCURsm-_8K?usp=sharing | N/A | N/A | None | Completed | Reviewd | None
4 | Splitting | 2024-07-28 | https://colab.research.google.com/drive/18Lo3BwAuiaqpXztKGXxk5LHCURsm-_8K?usp=sharing | N/A | N/A | None | Completed | Reviewd | None
5 | Data Visualization | 2024-07-28 | https://colab.research.google.com/drive/18Lo3BwAuiaqpXztKGXxk5LHCURsm-_8K?usp=sharing | N/A | N/A | None | Completed | Reviewd | None
6 | Prediction | 2024-07-28 | https://colab.research.google.com/drive/18Lo3BwAuiaqpXztKGXxk5LHCURsm-_8K?usp=sharing | N/A | N/A | None | Completed | Reviewd | None