## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Placement Predictor (Machine Learning) |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID | Faraj Momin (Intern ID -4039)
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Cloud Counselage
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2024-07-27 | Initial data collection had missing or incomplete entries | Software | No | Establish a data verification and validation process | Implement data checks and validation scripts | Project Developer | SOLVED | None
2 | 2024-07-28 | Difficulty integrating different data sources | Software | No | Plan for data integration earlier in the project | Create a comprehensive data integration strategy | Project Developer | SOLVED | None
3 | 2024-07-28 | Encountered bugs during model training | Software | No | Adopt a more rigorous testing framework | Implement unit tests and conduct regular code reviews | Project Developer | SOLVED | None
4 | 2024-07-28 | Overestimation of computational resources needed | Software | Yes | Reassess resource requirements periodically | Conduct regular resource usage evaluations | Project Developer | SOLVED | No. of time error gets.
5 | 2024-07-28 | Inaccurate initial model predictions | Software | No | Increase focus on model validation and tuning | Conduct thorough cross-validation and parameter tuning | Project Developer | SOLVED | None
6 | 2024-07-29 | Lack of clear documentation | Software | No | Maintain detailed project documentation from the start | Implement documentation standards and regular updates | Project Developer | SOLVED | None