## Project Schedule
IAC Internship Progra 2024 - Web Development Project Schedule |  |  |  |  | PROJECT NAME | Placement Predictor
[5 empty] | PROJECT MANAGER | Harshada Topale
PROJECT START DATE | 2024-07-27 |  |  |  | PROJECT START DATE | 2024-07-27
Project End Date | 2024-07-29 |  |  |  | PROJECT END DATE | 2024-07-29
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f |  |  |  |  | OVERALL PROGRESS | Completed
Activities | Task | Sub Task | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress
Project Initiation |  |  |  | 2024-07-27 | 2024-07-27 | 2024-07-27 | 1 Hrs | Completed | Done
| Define project scope | None | Project Developer | 2024-07-27 | 2024-07-27 | 2024-07-27 | 15 min | Completed | Done
| Conduct Feasibility Study | None | Project Developer | 2024-07-27 | 2024-07-27 | 2024-07-27 | 15 min | Completed | Done
| Develop Project Charter | None | Project Developer | 2024-07-27 | 2024-07-27 | 2024-07-27 | 15 min | Completed | Done
| Develop SRS DOCUMENT | None | Project Developer | 2024-07-27 | 2024-07-27 | 2024-07-27 | 15 min | Completed | Done
Project Planning |  |  |  | 2024-07-27 | 2024-07-27 | 2024-07-27 | 1 Hrs | Completed
| Define Project Scope | None | Project Developer | 2024-07-27 | 2024-07-27 | 2024-07-27 | 15 min | Completed | Done
| Develop Project Schedule | None | Project Developer | 2024-07-27 | 2024-07-27 | 2024-07-27 | 15 min | Completed | Done
| Risk Management Planning | None | Project Developer | 2024-07-27 | 2024-07-27 | 2024-07-27 | 15 min | Completed | Done
| Determine the resources required | None | Project Developer | 2024-07-27 | 2024-07-27 | 2024-07-27 | 15 min | Completed | Done
Project Building |  |  |  | 2024-07-28 | 2024-07-28 | 2024-07-28 | 10.5 Hrs | Completed | Done
| Data Loading For TASK 1 and task 2 | None | Project Developer | 2024-07-28 | 2024-07-28 | 2024-07-28 | 2 Hrs | Completed | Done
| Data Modeling FOR Task 1 & 2 | None | Project Developer | 2024-07-28 | 2024-07-28 | 2024-07-28 | 3.5 Hrs | Completed | Done
| Coding | None | Project Developer | 2024-07-28 | 2024-07-28 | 2024-07-28 | 5 Hrs
Project Testing |  |  |  | 2024-07-29 | 2024-07-29 | 2024-07-29 | 5 hrs | Completed | Done
| Unit testing | None | Project Developer | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2 hrs | Completed | Done
| Bug fixing and optimization | None | Project Developer | 2024-07-29 | 2024-07-29 | 2024-07-29 | 3 hrs | Completed | Done
Project Deployment |  |  |  | 2024-07-29 | 2024-07-29 | 2024-07-29 | 5 hrs | Completed | Done
| Setup deployment environment | None | Project Developer | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2.5 hrs | Completed | Done
| Deploy to production | None | Project Developer | 2024-07-29 | 2024-07-29 | 2024-07-29 | 1 hrs | Completed | Done
| Post-deployment testing | None | Project Developer | 2024-07-29 | 2024-07-29 | 2024-07-29 | 1.5 hrs | Completed | Done
Documentation & Submission |  |  |  | 2024-07-29 | 2024-07-29 | 2024-07-29 | 5.10 hrs | Completed | Done
| Create a project Report |  | Project Developer | 2024-07-29 | 2024-07-29 | 2024-07-29 | 5 hrs | Completed | Done
| Create a short 5 min video |  | Project Developer | 2024-07-29 | 2024-07-29 | 2024-07-29 | 10 min | Completed | Done
| Submit Project |  | Project Developer | 2024-07-29 | 2024-07-29 | 2024-07-29 |  | Completed | Done
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you